| NSBEAP (507) Annual Training-Planning for 2019 |
| --- |
| Date: Wednesday December 5, 2018 Time: 3:00 pm EST Join Zoom Meeting https://ksu.zoom.us/j/212094221 One tap mobile +16699006833,,212094221# US (San Jose) +16468769923,,212094221# US (New York) | Dial by your location +1 669 900 6833 US (San Jose) +1 646 876 9923 US (New York) Meeting ID: 212 094 221 Find your local number: https://zoom.us/u/a7IhDM9BU |
| Notes |
| Roll Call Regional Representation Attendees Subcommittee Representation Attendees R1: National Steering Committee- Lisa Ashenbrenner-Hunt R2: Ed Bakos (NJ) Annual Training – Jennifer Collins (IN) R 3: Lee Ann Briggs (PA) Education- Nancy Larson (KS) R4: Donovan Grimwood (TN) Promotion- R5: Annette Fulgenzi (IL) Technical -Donovan Grimwood (TN) R6: Awards -Renee Bashel (WI) R7: Jennifer Wittenburg (IA) Website – Nancy Larson (KS) R8: EPA – Paula Hoag R9: Eric Florio (NV) R10: Belinda Breidenbach (ID) Discussion: Logistics Conference Dates: May 14-16, 2019 Conference Location: Chicago, IL at U.S. EPA Region V Conference and Training Center 12th floor – Reserved by Andy Anderson -Region V – Current Regional Small Business Liaison (RSBL) Announcement to Save the Date? Yes, once the registration is set up; also ask who needs to speak for travel approval Registration- Registration on NSBEAP website? - Yes, but questions about if payment can be collected on website Registration fee this year to cover costs since U.S. EPA covers this training biennially Annette suggested a fee between $130-150 to cover food/beverage costs and additional awards –Nancy will check with Annette on how to set up payment Need to know what will be included in fee for travel approval Equipment needs- Laptops – don’t rely on EPA’s Projectors – in each training room? Screens in each room? Microphones available? WiFi needed – Definitely need to confirm – we had some issues at the Region V meeting there in November –Beef up WiFi – Ask Andy – How do we ensure it is functioning? Travel scholarships- Can we offer these this year?- $4,000 available for awards and travel scholarship Don’t need to speak to get scholarship SBEAP Awards - Awards will be coordinated by Renee Bashel. Open Awards- When? Open awards by late Dec/Early January Renee will send Nancy nomination forms for website Agenda Development- Monday night – NSC meeting? – yes, good to have some type of gathering night before. Tuesday or Wednesday night- Awards Ceremony? Depends on location of awards ceremony- State exhange on Tues night preferred Thursday – Possible training for providing P2 assessments – Trainer from IL, MI or OH – Assistance from Donna Twicker – U.S. EPA Region V, P2 (to include local site visits?) Training in morning –site visits in afternoon (Optional:Thursday afternoon – Combine P2 with Environmental Assessments including Air) Logistics? Obtain ideas from each Sub-Committee for agenda-How we run our programs? Various states on a panel; get a few ideas from each subcommittee and have them poll members to determine interes Annual report session? - yes NSC Strategy session –interactive session – follow up from last year – What progress did we make? Pull out two to work on Joan’s update Newcomer training Potential Speakers: Invite Region V Administrator- and Deputy Administrator – Alan Walts Invite current RSBLs –Panel? Regions 2, 3, 5,7 & 10 OAR/OAQPS administration Pew Research Center – Present on their final report? SBA Office of Advocacy-Les Davies and SBA Regional Director and Marketing Director. ECOS- EPA Smart Sector Program-follow-up conversation? Trade Associations- one of the top sessions people liked in 2018 Marketing session –Outreach from various states – panel and/or examples, one of top sessions people liked in 2018, could expand on that discussion Environmental Law Institute – Lisa will invite How do you evaluate compliance assistance – IA and KS How to get Outcomes from site visits – What states already get this? Info in annual report, Could we create consistency? Follow up/Action Items: Jennifer to follow up on Logistics of Conference space with Andy Anderson Nancy to follow up with Annette on Registration and Registration Fee needs Annette to obtain hotel block Renee to send Nancy Awards info Jennifer to start draft of training agenda and look at past year’s notes Sub-committees to obtain three ideas from their committee for speakers or sessions Next call: January 3, 2019 3-4pm EST (2-3 CT) |
| NSBEAP (507) Annual Training-Planning for 2019 Jan. 3, 2019 Notes Roll Call those highlighted were in attendance Regional Representation Attendees Subcommittee Representation Attendees R1: National Steering Committee- Lisa Ashenbrenner-Hunt R2: Ed Bakos (NJ) Annual Training – Jennifer Collins (IN) R 3: Lee Ann Briggs (PA) Education- Nancy Larson (KS) R4: Donovan Grimwood (TN) Promotion- Jennifer and others R5: Annette Fulgenzi (IL) Technical -Donovan Grimwood (TN) R6: Awards -Renee Bashel (WI) R7: Jennifer Wittenburg (IA) Website – Nancy Larson (KS) R8: EPA – Paula Hoag R9: Eric Florio (NV) R10: Belinda Breidenbach (ID) Discussion: Red font represents updates to topic discussed Logistics Conference Dates: May 14-16, 2019 Conference Location: Chicago, IL at U.S. EPA Region V Conference and Training Center 12th floor – Reserved by Andy Anderson -Region V – Current Regional Small Business Liaison (RSBL) Pending Hotel – Central Loop Hotel, block good until April 15, 2019 – rate $199; Lounge in main area could work as hospitality area, could host awards there too and get hotel to cater reasonably. Annette is working on getting a sponsor for awards food Annette is working on a logo design for conference Registration $150 would cover coffee, snacks, possible lunch and transportation for a site visit if needed. What happens to the extra funds? These would stay in Ill, but amount would be minimal. Announcement to Save the Date? Yes, sent out via main at least once and will send again once registration is up. Need to ask who needs to speak for travel approval Registration- Registration on NSBEAP website? – Registration and payment will be a two-step process, payment collected through a link on the registration. Possible process could include registration confirmation e-mail includes payment detail. When will payment be required? At least 30-days out if possible. Equipment needs- No new information Laptops – don’t rely on EPA’s Projectors – in each training room? Screens in each room? Microphones available? WiFi needed – Definitely need to confirm – we had some issues at the Region V meeting there in November –Beef up WiFi – Ask Andy – How do we ensure it is functioning? Travel scholarships- Can we offer these this year?- $4,000 available for awards and travel scholarship Don’t need to speak to get scholarship SBEAP Awards - Awards will be coordinated by Renee Bashel. Open Awards- When? January Articles already sent to ASBO and planned for ECOs Renee will send NL Tweets Agenda Development- in process, Jenifer will prepare for next meeting Monday night – NSC meeting? – yes, good to have some type of gathering night before. Tuesday or Wednesday night- Awards Ceremony? Depends on location of awards ceremony- State exhange on Tues night preferred Thursday – Possible training for providing P2 assessments – Trainer from IL, MI or OH – Assistance from Donna Twicker – U.S. EPA Region V, P2 (to include local site visits?) Training in morning –site visits in afternoon (Optional:Thursday afternoon – Combine P2 with Environmental Assessments including Air) Logistics? Obtain ideas from each Sub-Committee for agenda-How we run our programs? Various states on a panel; get a few ideas from each subcommittee and have them poll members to determine interes Annual report session? - yes NSC Strategy session –interactive session – follow up from last year – What progress did we make? Pull out two to work on Joan’s update Newcomer training – Ice breaker for entire group on day one similar to 2018. Identify newcomers, but no need to “pair” them with anyone specific; ribbon on name tag to indicate newcomer. Nancy will share with Education. They will facilitate this ice breaker. Potential Speakers: Who is assigned to secure speakers? Invite Region V Administrator- and Deputy Administrator – Alan Walts - Jennifer Invite current RSBLs –Panel? Regions 2, 3, 5,7 & 10 – Nancy will work with Paula on this Pew Research Center – Present on their final report? SBA Office of Advocacy-Les Davies and SBA Regional Director and Marketing Director.- Annette ECOS- Donovan – Compliance Assistance Workgroups topic? Green Books EPA Smart Sector Program-follow-up conversation - Jennifer OAQPS? Tony? Lisa will talk with Tony Trade Associations- one of the top sessions people liked in 2018 - Annette Marketing session –Outreach from various states – panel and/or examples, one of top sessions people liked in 2018, could expand on that discussion – Need a marketing company to review our materials and offer suggestions? Annette will look into. Environmental Law Institute – Lisa invited and they are interested in attending. Lisa will be talking with them again. What percent of air emissions are attributed to area sources? Annette How do you evaluate compliance assistance – IA and KS - Nancy How to get Outcomes from site visits – What states already get this? Info in annual report, Could we create consistency? Follow up/Action Items: Jennifer to follow up on Logistics of Conference space with Andy Anderson Nancy will f/u with Education Subcommittee to plan Newcomer session Nancy will work to get registration and awards posted Several have speaker contact duties Annette to obtain hotel block Jennifer to start draft of training agenda and look at past year’s notes Lisa will remind subcommittees to obtain three ideas from their committee for speakers or sessions Next call: Feb. 7, 2019 3-4pm EST (2-3 CT) |
| NSBEAP (507) Annual Training-Planning for 2019 Feb. 7, 2019 Notes Roll Call – those highlighted were in attendance Regional Representation Attendees Subcommittee Representation Attendees R1: National Steering Committee- Lisa Ashenbrenner-Hunt R2: Ed Bakos (NJ) Annual Training – Jennifer Collins (IN) R 3: Lee Ann Briggs (PA) Education- Nancy Larson (KS) R4: Donovan Grimwood (TN) Promotion- R5: Annette Fulgenzi (IL) Technical -Donovan Grimwood (TN) R6: Awards -Renee Bashel (WI) R7: Jennifer Wittenburg (IA) Website – Nancy Larson (KS) R8: EPA – Paula Hoag R9: Eric Florio (NV) R10: Belinda Breidenbach (ID) Discussion: Logistics Conference Dates: May 14-16, 2019 – actually starts the evening before, we should make sure to indicate on the registration and the website. Conference Location: Chicago, IL at U.S. EPA Region V Conference and Training Center 12th floor – Reserved by Andy Anderson -Region V – Current Regional Small Business Liaison (RSBL) Central Loop Hotel, block good until April 15, 2019 – rate $199; Lounge in main area could work as hospitality area, could host awards there too and get hotel to cater reasonably. If you find a cheaper rate it is OK to book separately. Annette is working on getting a sponsor for awards food Annette is working on a logo design for conference Registration $150 would cover coffee, snacks, possible lunch and transportation for a site visit if needed. What happens to the extra funds? These would stay in Ill, but amount would be minimal. Announcement to Save the Date? Yes, sent out via main at least once and will send again once registration is up. Need to ask who needs to speak for travel approval – so far only Lloyd Kirk. The Elephant and Castle – pub that will be used to host a Monday NSC and State Networking Exchange Registration- Update from Nancy/Annette Registration on NSBEAP website? – Registration and payment will be a two-step process, payment collected through a link on the registration. Possible process could include registration confirmation e-mail includes payment detail. Registration draft, Nancy will work with Annette to get it finalized. When will payment be required? At least 30-days out if possible. Equipment needs- Jennifer Laptops – don’t rely on EPA’s Projectors – in each training room? Screens in each room? Microphones available? WiFi needed – Definitely need to confirm – we had some issues at the Region V meeting there in November –Beef up WiFi – Ask Andy – How do we ensure it is functioning? Travel scholarships- $4,000 available for awards and travel scholarship Don’t need to speak to get scholarship SBEAP Awards - Awards will be coordinated by Renee Bashel. Awards are open until February 28 Articles already sent to ASBO and planned for ECOs Renee will send NL Tweets Agenda Development- Update from Jennifer – reviewed a separate draft agenda document Monday night – NSC meeting and Newcomer, yes, Education Subcommittee is planning Newcomer – is Annette working on securing location? The Elephant and Castle? Tuesday or Wednesday night- Awards Ceremony? Depends on location of awards ceremony- State exhange on Tues night preferred The Elephant and Castle? Thursday – Possible training for providing P2 assessments – Trainer from IL, MI or OH – Assistance from Donna Twicker – U.S. EPA Region V, P2 (to include local site visits?) Training in morning –site visits in afternoon (Optional:Thursday afternoon – Combine P2 with Environmental Assessments including Air) Logistics? Obtain ideas from each Sub-Committee for agenda-How we run our programs? Various states on a panel; get a few ideas from each subcommittee and have them poll members to determine interes Annual report session? – we can be flexible, Education is collecting votes for topics. NSC Strategy session –interactive session – follow up from last year – What progress did we make? Pull out two to work on Joan’s update – scheduled for Day 1 Newcomer training – Ice breaker for entire group on day one similar to 2018. Identify newcomers, but no need to “pair” them with anyone specific; ribbon on name tag to indicate newcomer. Nancy will share with Education. They will facilitate this ice breaker. Potential Speakers: Who is assigned to secure speakers? – see draft agenda for updates Invite Region V Administrator- and Deputy Administrator – Alan Walts - Jennifer Invite current RSBLs –Panel? Regions 2, 3, 5,7 & 10 – Nancy will work with Paula on this Pew Research Center – Present on their final report? SBA Office of Advocacy-Les Davies and SBA Regional Director and Marketing Director.- Annette ECOS- Donovan – Compliance Assistance Workgroups topic? Green Books EPA Smart Sector Program-follow-up conversation - Jennifer OAQPS? Tony? Lisa will talk with Tony Trade Associations- one of the top sessions people liked in 2018 - Annette Marketing session –Outreach from various states – panel and/or examples, one of top sessions people liked in 2018, could expand on that discussion – Need a marketing company to review our materials and offer suggestions? Annette will look into. Environmental Law Institute – Lisa invited and they are interested in attending. Lisa will be talking with them again. What percent of air emissions are attributed to area sources? Annette How do you evaluate compliance assistance – IA and KS - Nancy How to get Outcomes from site visits – What states already get this? Info in annual report, Could we create consistency? Follow up/Action Items: Jennifer to follow up on Logistics of Conference space with Andy Anderson Nancy will f/u with Education Subcommittee to plan Newcomer session and Paula regarding RSBL invites/panel Nancy will work with Annette to finalize registration and other page posts Several have speaker contact duties Annette will confirm hotel details and secure meal space for Monday NSC dinner and State gift exchange Jennifer will send draft agenda to Nancy to post Next call: Mar. 7, 2019 3-4pm EST (2-3 CT) |

NSBEAP (507) Annual Training-Planning for 2019 March 7, 2019 Agenda Roll Call – those highlighted were in attendance Regional Representation Attendees Subcommittee Representation Attendees R1: National Steering Committee- Lisa Ashenbrenner-Hunt (WI) R2: Ed Bakos (NJ) Annual Training – Jennifer Collins (IN) R 3: Lee Ann Briggs (PA) Education- Nancy Larson (KS) R4: Donovan Grimwood (TN) Promotion- Jennifer Collins, (ID) R5: Annette Fulgenzi (IL) Technical -Donovan Grimwood (TN) R6: Lloyd Kirk (OK) Awards -Renee Bashel (WI) R7: Jennifer Wittenburg (IA) Website – Nancy Larson (KS) R8: EPA – Paula Hoag R9: Eric Florio (NV) R10: Belinda Breidenbach (ID) Discussion: Logistics Conference Dates: May 13-16, 2019 Conference Location: Chicago, IL at U.S. EPA Region V Conference and Training Center 12th floor – Reserved by Andy Anderson -Region V – Current Regional Small Business Liaison (RSBL) Central Loop Hotel, block good until April 15, 2019 – rate $199; Lounge in main area could work as hospitality area, could host awards there too and get hotel to cater reasonably. If you find a cheaper rate it is OK to book separately. Logo completed – Which ones do we want to use? Annette. Discussed, but Annette has a plan. She will use national logo on some reusable items so we have items, banners that can be used for other events. Registration $150 would cover coffee, snacks, possible lunch and transportation for a site visit if needed. Do invited speakers need to pay? No, they can register but do not need to pay. Announcement to Save the Date? Yes, sent out via main at least once and will send again once registration is up. Sent twice so far and can be ongoing biweekly until training. Need to ask who needs to speak for travel approval – so far only Lloyd Kirk. Registration- Update from Nancy/Annette Registration is on the NSBEAP website – Registration and payment is be a two-step process, payment collected through a link on the registration. Equipment needs- Jennifer Laptops – Jennifer says we will have our own laptops Projectors – in each training room? Screens in each room? Microphones - yes Speakers – Jennifer will check on this. WiFi needed – Confirmed per Jennifer Travel scholarships-Nancy $4,000 available for awards and travel scholarship – able to increase scholarships by $1000 this year. Three applications to date. Don’t need to speak to get scholarship SBEAP Awards – Renee Award nominations received/Process – several applicants and in process of scoring applications now. Ordering awards – Renee is looking for a resource, Annette will forward one option in Ill. Agenda Development- Update from Jennifer – see draft agenda document Monday night – NSC meeting and Newcomer, yes, Education Subcommittee is planning Newcomer – Location is pending. Annette will look into cost for reserving the reception area and a possible separate room at an adjacent resturant. Tuesday or Wednesday night- Awards Ceremony? Depends on location of awards ceremony- State exhange on Tues night preferred The Elephant and Castle for state exchange and reception area at hotel for awards – reservation pending per Annette Thursday – Possible training for providing P2 assessments – Trainer from IL, MI or OH – Training in morning –site visits in afternoon – this is still pending due to P2 meeting conflict Obtain ideas from each Sub-Committee for agenda-How we run our programs? Various states on a panel; get a few ideas from each subcommittee and have them poll members to determine interes Annual report session? – we can be flexible, Education is collecting votes for topics. NSC Strategy session –interactive session – follow up from last year – What progress did we make? Pull out two to work on Joan’s update – scheduled for Day 1-Paula let us know that Joan will not be there. Newcomer training – Ice breaker for entire group on day one similar to 2018. Identify newcomers, but no need to “pair” them with anyone specific; ribbon on name tag to indicate newcomer. Nancy will share with Education. They will facilitate this ice breaker. Potential Speakers: Who is assigned to secure speakers? – see draft agenda Invite Region V Administrator- and Deputy Administrator – Alan Walts - Jennifer Invite current RSBLs –Panel? Regions 2, 3, 5,7 & 10 – Paula has sent a formal invite, but has only heard back from one region so far. She will follow-up. Pew Research Center – Present on their final report? SBA Office of Advocacy-Les Davies and SBA Regional Director and Marketing Director.- Annette ECOS- Donovan – Compliance Assistance Workgroups topic? Green Books EPA Smart Sector Program-follow-up conversation - Jennifer OAQPS? Tony? Potentially our new OAQPS new liaison – Rhonda Wright Trade Associations- one of the top sessions people liked in 2018 - Annette Marketing session –Outreach from various states – panel and/or examples, one of top sessions people liked in 2018, could expand on that discussion – Need a marketing company to review our materials and offer suggestions? Annette will look into. Environmental Law Institute – Lisa invited and they are interested in attending. Lisa has not heard back. What percent of air emissions are attributed to area sources? Annette? How do you evaluate compliance assistance, get outcome metrics from technical assistance – IA and KS – Nancy may try to combine with SBA metriics session Follow up/Action Items from last meeting: Annette will confirm hotel reception reservations and location for networking dinner Jennifer to follow up on room speakers, R5 air person and MI P2 training. Jennifer will connect SBA with Nancy with regard to metric session Nancy will f/u with Education Subcommittee to plan Newcomer session and with metrics SBA contact Nancy will f/u with Paula on RSBLs Several have speaker contact duties Jennifer will send draft agenda to Nancy to post Next call: Do we need to meet every two weeks now? Yes, Jennifer will send out meeting Doodle.

NSBEAP (507) Annual Training-Planning for 2019 March 22, 2019 Agenda Roll Call – those highlighted were in attendance Regional Representation Attendees Subcommittee Representation Attendees R1: National Steering Committee- Lisa Ashenbrenner-Hunt (WI) R2: Ed Bakos (NJ) Annual Training – Jennifer Collins (IN) R 3: Lee Ann Briggs (PA) Education- Nancy Larson (KS) R4: Donovan Grimwood (TN) Promotion- Jennifer Collins, (ID) R5: Annette Fulgenzi (IL) Technical -Donovan Grimwood (TN) R6: Lloyd Kirk (OK) Awards -Renee Bashel (WI) R7: Jennifer Wittenburg (IA) Website – Nancy Larson (KS) R8: EPA – Paula Hoag R9: Eric Florio (NV) R10: Belinda Breidenbach (ID) Discussion: Logistics Conference Dates: May 13-16, 2019 Conference Location: Chicago, IL at U.S. EPA Region V Conference and Training Center 12th floor – Reserved by Andy Anderson -Region V – Current Regional Small Business Liaison (RSBL) Central Loop Hotel, block good until April 15, 2019 – rate $199; Lounge in main area could work as hospitality area, could host awards there too and get hotel to cater reasonably. If you find a cheaper rate it is OK to book separately. 3/15 Webpage updated with some new details from Annette. OK to book only 3 of 4 nights. Annette will provide clarification. Logo completed – Which ones do we want to use? Annette. Discussed, but Annette has a plan. She will use national logo on some reusable items so we have items, banners that can be used for other events. Registration $150 would cover coffee, snacks, possible lunch and transportation for a site visit if needed. Do invited speakers need to pay? No, they can register but do not need to pay. 3/22 20 people registered Announcement to Save the Date? Yes, sent out via main at least once and will send again once registration is up. Sent twice so far and can be ongoing biweekly until training. Need to ask who needs to speak for travel approval – so far only Lloyd Kirk. Registration- Update from Nancy/Annette Registration is on the NSBEAP website – Registration and payment is be a two-step process, payment collected through a link on the registration. 3/22 20 people registered. Equipment needs- Jennifer Laptops – Jennifer says we will have our own laptops Projectors – in each training room? Yes Screens in each room? Yes Microphones – yes, but not needed in small room Speakers – if use of microphone than speakers WiFi needed – Confirmed per Jennifer – EPA still working on confirming it is accessable for our meeting; names and phone numbers for all attendees will need to be forwarded. Food is OK in the rooms Travel scholarships-Nancy $4,000 available for awards and travel scholarship – able to increase scholarships by $1000 this year. Three applications to date. Don’t need to speak to get scholarship SBEAP Awards – Renee – due today, Lloyd finishing for R6, Renee has award hardware source. Agenda Development- Update from Jennifer – see draft agenda document Monday night resturant – having difficulty securing without a fee. Still working on. Tuesday or Wednesday night- Awards Ceremony? Depends on location of awards ceremony- State exhange on Tues night preferred The Elephant and Castle for state exchange and reception area at hotel for awards – reservation pending per Annette Thursday – Possible training for providing P2 assessments – Trainer from IL, MI or OH – Training in morning –site visits in afternoon – this is still pending due to P2 meeting conflict Annual report session? – Plan for 30-minute overview. NSC Stradegy : Need five people at each topic - RSBL, OAQPS, Promotion, Guidance, funding Joan’s update – 3/22 scheduled for Day 1-Paula and Elnora will attend. Newcomer training – Ice breaker for entire group on day one similar to 2018. Identify newcomers, but no need to “pair” them with anyone specific; ribbon on name tag to indicate newcomer. Pending Education meeting 3/26. Potential Speakers: Who is assigned to secure speakers? – see draft agenda Invite Region V Administrator- and Deputy Administrator – Jennifer RSBLs session – Paula not sure how many can attend, especially due to P2 meeting conflict. May want to shift this session. SBA Office of Advocacy-Les Davies and SBA Regional Director and Marketing Director.- Annette OAQPS? Tony? 3/22 – Rhonda Wright is scheduled. Who has reached out to her. Paula recommends that we plan a session that how they can partner with SBEAPs. Trade Associations- one of the top sessions people liked in 2018 – Annette and Renee Marketing session –Outreach from various states – panel secured, session moving to Wednesday. Not sure if we will use an outside marketing person too. What do people want to do. What percent of air emissions are attributed to area sources? Annette? How do you evaluate compliance assistance, get outcome metrics from technical assistance – IA and KS – Nancy may try to combine with SBA metriics session Follow up/Action Items from last meeting: Annette will confirm location for networking dinner Someone needs to f/u with Tony to ensure Rhonda Wright is confirmed and we expand session to brainstorm how we can work together. Formal invite needs to go to RSBLs – R3, R5, R7, R10 – Lisa will draft and e-mail and send invite to RSBLs and Paula will a Renee and Annette working to secure trade association panel Jennifer will e-mail Paula topic we need help with, specifically R5 OAR to present Tuesday at 1:15pm.and Tuesday session. Jennifer will send draft agenda to Nancy to post Jennifer will confirm we have room third day Nancy will f/u with Education Subcommittee to plan Newcomer session and with metrics SBA contact Nancy will post updated agenda and minutes Nancy will push out registration and pay of registration and hotel April 13th Next call: Apirl 4, at 1:30pm EST

NSBEAP (507) Annual Training-Planning for 2019 April 4, 2019 Agenda Roll Call – those highlighted were in attendance Regional Representation Attendees Subcommittee Representation Attendees R1: National Steering Committee- Lisa Ashenbrenner-Hunt (WI) R2: Ed Bakos (NJ) Annual Training – Jennifer Collins (IN) R 3: Lee Ann Briggs (PA) Education- Nancy Larson (KS) R4: Donovan Grimwood (TN) Promotion- Jennifer Collins, (ID) R5: Annette Fulgenzi (IL) Technical -Donovan Grimwood (TN) R6: Lloyd Kirk (OK) Awards -Renee Bashel (WI) R7: Jennifer Wittenburg (IA) Website – Nancy Larson (KS) R8: EPA – Paula Hoag Others: Jennifer Lipkin, Tony Pendola R9: Eric Florio (NV) R10: Belinda Breidenbach (ID) Discussion: Logistics Conference Dates: May 13-16, 2019 Conference Location: Chicago, IL at U.S. EPA Region V Conference and Training Center 12th floor – Reserved by Andy Anderson -Region V – Current Regional Small Business Liaison (RSBL) Confirmed. Central Loop Hotel, block good until April 15, 2019 – rate $199; Lounge in main area could work as hospitality area, could host awards there too and get hotel to cater reasonably. If you find a cheaper rate it is OK to book separately. 3/15 Webpage updated with some new details from Annette. OK to book only 3 of 4 nights. Annette will provide clarification. Logo completed – Which ones do we want to use? Annette. Discussed, but Annette has a plan. She will use national logo on some reusable items so we have items, banners that can be used for other events. Registration $150 would cover coffee, snacks, possible lunch and transportation for a site visit if needed. Do invited speakers need to pay? No, they can register but do not need to pay. 4/3, 37 pre-registered, 22 paid Video offered by EPA, do we want to use this or Zoom? Jennifer will connect Nancy with EPA contact to consult. Registration- Update from Nancy/Annette Registration is on the NSBEAP website – Registration and payment is be a two-step process, payment collected through a link on the registration. 3/22 20 people registered. Equipment needs- Jennifer: Secured Travel scholarships-Nancy $4,000 available for awards and travel scholarship – able to increase scholarships by $1000 this year. Three applications to date. Eight awards given to people in eight different states. Five of which are newcomers. SBEAP Awards – Renee has notified all awardees and asked business to contact if needed scholarships. Businesses from Indiana coming, KS trying to attend. Agenda Development- Updates Monday night resturant – Renee is close to having this secured. Agenda updated Potential Speakers: Two primary speakers still pending - Technical session on surface coating – Mark Stoddard PFOS/PFAS – need to secure EPA speaker for update on recent action plan – Jennifer will reach out. Acceptance by EPA Keynote – Jennifer and Lisa Trade association panel – Renee may be able to secure a few additional RSBLs session – Paula not sure how many can attend, At least one from Region 7 attending, no session planned at this time. Follow up/Action Items Jennifer and Lisa - Acceptance by EPA Keynote Jennifer - connect Nancy with EPA rep regarding video streaming of event. Jennifer - need to secure EPA speaker for update on PFOS/PFAS action plan Lisa – Send formal invite needs to go to RSBLs – R3, R5, R7, R10 – Mark Stoddard - Secure surface coating speakers Renee – Secure Monday night dinner location Renee - working to secure trade associations for panel Nancy - post updated agenda and minutes Nancy - will push out registration and pay of registration and hotel April 13th Next call: Apirl 18, at 1:30pm Central and 2:30 pm EST

NSBEAP (507) Annual Training-Planning for 2019 April 18, 2019 Agenda Roll Call – those highlighted were in attendance Regional Representation Attendees Subcommittee Representation Attendees R1: National Steering Committee- Lisa Ashenbrenner-Hunt (WI) R2: Ed Bakos (NJ) Annual Training – Jennifer Collins (IN) R 3: Lee Ann Briggs (PA) Education- Nancy Larson (KS) R4: Donovan Grimwood (TN) Promotion- Jennifer Collins, (ID) R5: Annette Fulgenzi (IL) Technical -Donovan Grimwood (TN) R6: Lloyd Kirk (OK) Awards -Renee Bashel (WI) R7: Jennifer Wittenburg (IA) Website – Nancy Larson (KS) R8: EPA – Paula Hoag Others: Jennifer Lipkin, Tony Pendola R9: Eric Florio (NV) R10: Belinda Breidenbach (ID) Discussion: Logistics Conference Dates: May 13-16, 2019 Conference Location: Chicago, IL at U.S. EPA Region V Conference and Training Center 12th floor – Reserved by Andy Anderson -Region V – Current Regional Small Business Liaison (RSBL) Confirmed. Central Loop Hotel, block good until April 15, 2019 – rate $199; Lounge in main area could work as hospitality area, could host awards there too and get hotel to cater reasonably. If you find a cheaper rate it is OK to book separately. 3/15 Webpage updated with some new details from Annette. OK to book only 3 of 4 nights. Annette will provide clarification. Logo completed – Which ones do we want to use? Annette. Discussed, but Annette has a plan. She will use national logo on some reusable items so we have items, banners that can be used for other events. Registration $150 would cover coffee, snacks, possible lunch and transportation for a site visit if needed. Do invited speakers need to pay? No, they can register but do not need to pay. 4/18, 48 pre-registered, 41 paid Video offered by EPA, do we want to use this or Zoom? Using Zoom Registration- Update from Nancy/Annette Registration is on the NSBEAP website – Registration and payment is be a two-step process, payment collected through a link on the registration. Equipment needs- Jennifer: Secured Travel scholarships-Nancy $4,000 available for awards and travel scholarship – able to increase scholarships by $1000 this year. Three applications to date. Eight awards given to people in eight different states. Five of which are newcomers. SBEAP Awards – Renee has notified all awardees and asked business to contact if needed scholarships. Businesses from Indiana coming, KS trying to attend. Agenda Development- Updates Monday night resturant – Catus Bar and Grill Newcomers – Update from Belinda – Networking session / Meet Newcomers – Survey related to SBEAPs-Have each state bring 50 business cards Potential Speakers: Two primary speakers still pending - Technical session on surface coating – Mark Stoddard PFOS/PFAS – need to secure EPA speaker for update on recent action plan – Jennifer will reach out. Acceptance by EPA Keynote – Jennifer and Lisa Trade association panel – Renee may be able to secure a few additional RSBLs session – Paula not sure how many can attend, At least one from Region 7 attending, no session planned at this time. To fill time slot for OAR Case studies from Annual report – Success stories from various states Back pocket speeches to fill in vacancies- Belinda at recent conference had slide decks as back up MEPs – Annette Follow up/Action Items Jennifer - need to secure EPA speaker for OAR update Jennifer – send out survey to participants for their information for Wi-Fi access Annette – confirm marketing session format and title Renee - working to secure trade associations for panel Nancy – Confirm Zoom information with Catherine Tunis Nancy - post updated agenda and minutes Next call: May 2, at 1:30pm Central and 2:30 pm EST --------------------------------------------------------------------------------------------------------------------------------------------------------------- NSBEAP (507) Annual Training-Planning for 2019 May 2, 2019 Agenda Roll Call – those highlighted were in attendance Regional Representation Attendees Subcommittee Representation Attendees R1: National Steering Committee- Lisa Ashenbrenner-Hunt (WI) R2: Ed Bakos (NJ) Annual Training – Jennifer Collins (IN) R 3: Lee Ann Briggs (PA) Education- Nancy Larson (KS) R4: Donovan Grimwood (TN) Promotion- Jennifer Collins, (ID) R5: Annette Fulgenzi (IL) Technical -Donovan Grimwood (TN) R6: Lloyd Kirk (OK) Awards -Renee Bashel (WI) R7: Jennifer Wittenburg (IA) Website – Nancy Larson (KS) R8: EPA – Paula Hoag Others: Jennifer Lipkin, Tony Pendola R9: Eric Florio (NV) R10: Belinda Breidenbach (ID) Discussion: Logistics: Monday night – Offically starts at 6pm, but happy hour starts at 4pm, so come early to be ready to start at 6pm. Resturant closes at 8pm. We will use Jennifer’s laptop as the presenter laptop Zoom sessions: Day 1: 12:30pm surface coating and 1:30pm Catherine Tunis OECA Day 2: 11:15 am evaluating compliance assistance and 2pm PFOS/PFAS Day 3: 10am –ISTC P2 process from conception to delivery Day 1 – all items in the room are coordinated and confirmed. Nametag pick up and coffee starts at 8am. Paula not able to secure a speaker to talk about air quality program “overall.” Jennifer will reach out to R5. One of the EPA compliance inspectors will be able to join us for the NESHAP session. Just using Zoom, not video taping via EPA’s intranet. Lisa and Belinda will need large tablets and markers – Indiana is driving and will bring the large tablets and markers. State networking event is set Day 2 – Need to make some adjustments to a few sessions PTE session – Donovan facilitating Awards session is all set. Day 3 All set Agenda notes – added directly to the agenda Last meeting is Wednesday May 8 at 12:30pm central; 1:30pm eastern